## Overall
NEW COMMUNITY HALL WOOD HOUSE
PROGRAMME
|  |  | -7 | -6 | -5 | -4 | -3 | -2 | -1 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
|  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY | 5: FEBRUARY; 9: MARCH; 13: APRIL; 17: MAY; 22: JUNE; 26: JULY; 31: AUGUST; 35: SEPT
|  |  | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11
1 | Parish Sign off of orders | bar: NOVEMBER 21 to NOVEMBER 28
2 | Demolition Order |  | NOVEMBER 28: 2
3 | Asbestos Notice Period |  | DECEMBER 5: 3
4 | Demolition | bar: DECEMBER 5 to JANUARY 16
5 | Main Contractor Order | bar: DECEMBER 5
6 | Steel Lead time 12 wks |  | MARCH 13: 6
7 | Secure Site |  | JANUARY 30: 7
8 | Prepare site for excavation of foundations | bar: JANUARY 30
9 | Foundations |  | MARCH 6: 9
10 | Erection of Steel |  | MARCH 20: 10
11 | Construction of Block Walls |  | APRIL 3: 11
12 | Fitting of insulated roof |  | APRIL 17: 12
13 | Drainage |  | APRIL 17: 13
14 | Beam and block floor and concrete flooring |  | MAY 1: 14
15 | Internal walls |  | MAY 1: 15
16 | 1st Fix Electrical, Plumbing, Joiners |  | MAY 15: 16
17 | Windows and Doors |  | MAY 15: 17
18 | External cladding |  | MAY 29: 18
19 | Plastering |  | MAY 29: 19
20 | Flooring |  | JUNE 12: 20
21 | Toilets |  | JUNE 12: 21
22 | Kitchen |  | JUNE 19: 22
23 | 2nd Fix Electrics, Plumbing and Joinery |  | JULY 3: 23
24 | Cupboards |  | JULY 3: 24
25 | Decoration |  | JULY 17: 25
26 | Testing |  | JULY 17: 26
27 | Snagging |  | JULY 24: 27
28 | Handover | bar: JULY 24
29 | COMPLETION | bar: JULY 31 to SEPT 11
CASH FLOW
FOUNDATIONS |  | 55000 | JANUARY 30: 25000; FEBRUARY 27: 30000
FLOOR SLAB |  | 30000 | APRIL 24: 20000; MAY 29: 10000
MASONRY & CLADDING |  | 65000 | MARCH 27: 20000; APRIL 24: 20000; MAY 29: 25000
STEELWORK |  | 60000 | DECEMBER 19: 50000; FEBRUARY 27: 10000
ROOF |  | 60000 | MARCH 27: 30000; APRIL 24: 30000
FASCIA, GUTTERS & DOWNPIPES |  | 5000 | MAY 29: 5000
PLASTERWORK |  | 15000 | MAY 29: 10000; JUNE 26: 5000
CEILINGS |  | 10000 | MAY 29: 5000; JUNE 26: 5000
WINDOWS, DOORS AND VELUX |  | 30000 | APRIL 24: 20000; MAY 29: 10000
JOINERY |  | 5000 | MAY 29: 1000; JUNE 26: 4000
KITCHEN UNITS |  | 5000 | MAY 29: 5000
PAINTING |  | 10000 | JUNE 26: 5000; JULY 31: 5000
TILING |  | 5000 | JUNE 26: 2500; JULY 31: 2500
FLOOR FINISHES |  | 10000 | JULY 31: 10000
PLUMBING WORKS |  | 7500 | MAY 29: 3000; JUNE 26: 4000; JULY 31: 500
ELECTRICAL WORKS |  | 7500 | MAY 29: 3000; JUNE 26: 4000; JULY 31: 500
EXTERNAL WORKS |  | 1500 | JULY 31: 1500
SERVICES |  | 2000 | JULY 31: 2000
|  | 383500 | NOVEMBER 21: 0; DECEMBER 19: 50000; JANUARY 30: 25000; FEBRUARY 27: 40000; MARCH 27: 50000; APRIL 24: 90000; MAY 29: 77000; JUNE 26: 29500; JULY 31: 22000